## Blad1
| April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | Nov. |  |  |  | Dec
Calendar week | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49
Thesis week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
0. Proposal
Introductory meeting
Writing first draft
Writing second draft
Start meeting
Writing possible third draft
1. Literature study
Analysis and comparison of existing approaches
Requirements analysis
Quantifying user values
Finalize literature study (D1) & Plan for full thesis project (D2) | [14 empty] | D1/2
2. Initial extended model design
Defining the approach
Rewriting and/or combining existing implementations
Extending model with user values
3. Implementing model
Translating the model definition to code
Define ways to prompt for, analyze and store user input
Fix bugs
4. Model analysis
Analyze model results and errors
Manual tweaking
Testing
Performance reporting
5. Final reporting
Reporting (D3) | [34 empty] | D3
Presentation (P) | [34 empty] | P