## Blad1
| April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | Nov. |  |  |  | Dec
Calendar week | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Thesis week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
0. Proposal | [6 empty] | HOLIDAY |  |  |  | SURGERY AND RECOVERY
Introductory meeting
Writing first draft
Writing second draft
Start meeting
Writing possible draft
1. Literature study
Analysis and comparison of existing approaches
Requirements analysis
Feasibility analysis
Combine papers for basis model
2. Initial extended model design
Defining the initial approach
Rewriting ML activity clustering
Connecting user values to activities
Obtain sample data for user values (+ crowdsourcing)
Combining clustering with user values
3. Implementing conceptual model
Translating the model definition to code
Statistical analysis and manual improvement
4. Usability extension
Write middleware between activity logs and model
Implement or combine with UI for user input
User testing
5. Final reporting
Reporting (D3) | [37 empty] | D3
Presentation (P) | [37 empty] | P
Deadlines | [20 empty] | M |  |  |  | C