## Blad1
| April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | Nov.
Calendar week | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46
Thesis week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
0. Proposal
Introductory meeting
Writing first draft
Writing second draft
Start meeting
1. Literature study
Analysis and comparison of existing approaches
Deconstructing goals
Finalize literature study (D1) & Plan for full thesis project (D2) | [10 empty] | D1/2
2. Initial model design
Defining the approach
Formalizing the ADL representation
Formalizing value representation
Formalizing norm representation
Formalizing goal representation
Prepare method to determine appropriate times from model
3. Implementing model
Translating the model definition to code
Define ways to prompt for, analyze and store user input
Fix bugs
4. Model analysis
Analyze model results and errors
Use manual testing and result analysis to improve the model
Performance analysis
5. Final reporting
Reporting (D3) | [31 empty] | D3
Presentation (P) | [31 empty] | P